## Sprint1_2weeks
Feature | Type | Status | Remarks
Custom test instruction and candidates should agree before registering for assessment | Development | not started
Provide password protect or OTP for the assessment | Development | done
Save candidates data and assessment data in the backend | Development | done
Should be able to give test access for specific duration (Start Date/Time & End Date/Time) | Development | done
Should be able to fetch results report based on any criteria, ideally by changing the cut-off percentage anytime | Development | not started
Provision to choose questions based on technology, skills, tags; in search bar | Development | not started
Provision to give custom score based on question type | Development | wip
Randomize questions & options | Development | later
Provision to create and conduct Skill Based assessment | Development | done
Question should have bold/ Italic/ underline option. | Development | done
Provision to have code based MCQ question and answers | Development | not started
Provision for candidates to move from one question to another by just clicking on the question no. | Development | not started
Resume the test from where it stopped; if there is any issue that occurs during the assessment. | Development | wip
Yaksha Logo across all test links | Design | not started | Need a new logo?
Enter support email address that is applicable for resolution through Unified Help Desk and Yaksha Operations Team | Design | not started | Give the Ops Email id
Remove mobile number from UI | Design | not started
Check the Login details of Codeacademy.com or any other websites to provide center of the page or top of the mind recall of data capture. the color should be sleek than simple behind this entry level | Design | not started
sign in details to be moved to the center of the page | Design | not started
all of these must be represented in a standard document format for "click to start the test" inside which all the test information should be present including duration, test name, number of questions and test administrator | Design | not started